## Excel Gantt Chart Template
Gantt Chart
SOEN6611 - Project Proposed Timeline |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2019-02-06 | 2019-02-11 | Milestone 2 Draft submission | 6
2019-02-11 | 2019-02-13 | In depth analysis of Related Research Papers | 3
2019-02-12 | 2019-02-13 | Comparison with our studies | 2
2019-02-13 | 2019-02-13 | POD Session | 1
2019-02-13 | 2019-02-13 | Identify Limitations of the Proposed work | 1
2019-02-14 | 2019-02-14 | Scope of Improvement | 1
2019-02-15 | 2019-02-15 | Team Progress Meeting | 1
2019-02-15 | 2019-02-15 | Draft Preparation | 1
2019-02-16 | 2019-02-16 | Final Draft Review & Changes | 1
2019-02-17 | 2019-02-17 | Milestone 3 Draft submission | 1
Metric Development and Implementation
2019-02-18 | 2019-02-23 | Internal Metrics | 6
2019-02-19 | 2019-02-24 | Sample Metric Computation | 6
2019-02-20 | 2019-02-20 | POD Session | 1
2019-02-24 | 2019-02-28 | Metric Implementation | 4
2019-02-27 | 2019-02-27 | POD Session | 1
2019-03-01 | 2019-03-01 | Metric Testing | 1
2019-03-03 | 2019-03-03 | Team Progress Meeting | 1
EXTERNAL METRICS
2019-03-04 | 2019-03-06 | Chage control | 4
2019-03-06 | 2019-03-06 | POD Session | 1
2019-03-07 | 2019-03-07 | Unit Testing & Integration | 2
2019-03-08 | 2019-03-09 | Bug Report & Fixing | 2
2019-03-10 | 2019-03-12 | Data Collection in Spreadsheet | 3
2019-03-13 | 2019-03-13 | POD Session | 1
2019-03-14 | 2019-03-14 | Team Progress Meeting | 1
2019-03-14 | 2019-03-16 | Draft Preparation | 4
2019-03-17 | 2019-03-17 | Final Draft Review & Changes(if any) | 1
2019-03-18 | 2019-03-18 | Milestone 4 Draft submission | 1
STATISTCAL TESTING
2019-03-19 | 2019-03-20 | Correlation Analysis | 2
2019-03-20 | 2019-03-20 | POD Session | 1
2019-03-20 | 2019-03-21 | Regression Testing & Bug Fixing | 2
2019-03-22 | 2019-03-22 | Project Deviation Evaluation | 1
2019-03-23 | 2019-03-23 | Test result analysis | 1
2019-03-24 | 2019-03-24 | Team Meeting(Hypothesis review based on test result) | 1
2019-03-24 | 2019-03-24 | Draft Preparation | 1
2019-03-25 | 2019-03-25 | Final Draft Review & Changes (if any) | 1
2019-03-26 | 2019-03-26 | Milestone 5 Draft Submission
FINAL PHASE
2019-03-27 | 2019-04-02 | Prepare Presentation | 5
2019-03-27 | 2019-03-27 | POD Session | 1
2019-03-28 | 2019-04-02 | Research Paper Writing | 4
2019-04-03 | 2019-04-03 | POD Session | 1
2019-04-04 | 2019-04-05 | Initial draft of Research Paper | 2
2019-04-06 | 2019-04-06 | Paper review POD(Possibility) | 1
2019-04-08 | 2019-04-08 | Milestone 5 Final report & Presentation
Make impressive PowerPoint Gantt charts for important meetings. |  |  |  | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Trial Edition.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of
PowerPoint. Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce a PowerPoint Gantt chart slide.

## Excel Timeline Template
Excel Timeline Template
Enter Your Project Details Here
DATE | DESCRIPTION | POSITION
2018-05-10 | Kick Off | 1
2018-06-07 | Milestone 1 | 2
2018-07-21 | Milestone 2 | 1
2018-08-01 | Checkpoint A | 4
2018-09-20 | Milestone 3 | 3
2018-10-30 | Milestone 4 | 2
2018-12-20 | Checkpoint B | 3
2019-01-30 | Milestone 5 | 4
2019-02-10 | Milestone 6 | 1
2019-03-30 | Milestone 7 | 2 |  | `
2019-05-20 | Checkpoint C | 3
2019-05-30 | Sign Off | 1
Make beautiful timelines in PowerPoint for important meetings. |  |  | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
https://www.officetimeline.com/download
Note on D6: Excel Project Timeline Tip: The position values vary the height of your Milestones and are used to prevent text overlap. Using negative numbers will place Milestones labels below the timeband. If you position a Milestone below the timeband click on its label in the chart to set its Label Position to below.
Note on B17: Excel Project Timeline Tip: To add more Milestones, insert new rows into this table and then use the Select Data field to update your Series as shown in step # 3 here: https://www.officetimeline.com/make-timeline/excel
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Free Trial.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint.
Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce your timeline slide.

## Sheet1
43502
43563